## RS Gantt Chart
Courtesy of:
PROJECT TITLE
Project Lead
|  |  | Begin Projects: | 2019-07-01
|  |  | Scroll to Project Week: | 1 | [10 empty] | Week of: June 30, 2019 | [6 empty] | Week of: July 07, 2019 | [6 empty] | Week of: July 14, 2019 | [6 empty] | Week of: July 21, 2019 | [6 empty] | Week of: July 28, 2019
DONE |  | TASK | OWNER | START DATE | FINISH DATE | DAYS DURATION | WORK DAYS | DAYS DONE | DAYS REMAINING | DONE % | PRIORITY | FLAG | STAR | SPRINT / MILESTONE | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04
[15 empty] | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
| CLIENT DELIVERABLE |  |  | 2019-07-01 | 2019-12-31 | 183 | 132
1 |  | Task 1 | Management | 2019-07-01 | 2019-07-05 | 5 | 5 | 5 | 0 | 100% | 0 | 0 | 1 | Sprint 1
1 |  | Task 2 | Content | 2019-07-01 | 2019-07-14 | 14 | 10 | 14 | 0 | 100% | 0 | 0 | 1 | Sprint 1 | bar: 2019-07-06
0.38462 |  | Task 3 | Design | 2019-07-07 | 2019-08-01 | 26 | 19 | 10 | 16 | 38.46% | 2 | 2 | 0.38462 | Sprint 1
1 |  | Task 4 | Digital | 2019-07-02 | 2019-07-02 | 1 | 1 | 1 | 0 | 100% | 2 | 2 | 1 | Sprint 1
0 |  | Task 5 | Development | 2019-07-15 | 2019-07-15 | 1 | 1 | 0 | 1 | 0% | 3 | 3 | 0 | Sprint 1
0.006135 |  | Task 6 | Social | 2019-07-22 | 2019-12-31 | 163 | 117 | 1 | 162 | 0.6135% | 4 | 3 | 0.006135 | Sprint 1
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 1
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 1 | bar: 2019-07-13
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 1
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 1
Insert new rows ABOVE this line
| CLIENT DELIVERABLE |  |  | 2019-07-01 | 2019-12-31 | 183 | 132
1 |  | Task 1 | Management | 2019-07-01 | 2019-07-05 | 5 | 5 | 5 | 0 | 100% | 1 | 1 | 1 | Sprint 2
0.93333 |  | Task 2 | Content | 2019-07-01 | 2019-07-15 | 15 | 11 | 14 | 1 | 93.33% | 1 | 1 | 0.93333 | Sprint 2
0.3125 |  | Task 3 | Design | 2019-08-01 | 2019-09-01 | 32 | 22 | 10 | 22 | 31.25% | 2 | 2 | 0.3125 | Sprint 2
0 |  | Task 4 | Digital | 2019-07-15 | 2019-09-01 | 49 | 35 | 0 | 49 | 0% | 2 | 2 | 0 | Sprint 2
0.090909 |  | Task 5 | Development | 2019-08-22 | 2019-09-01 | 11 | 7 | 1 | 10 | 9.091% | 3 | 3 | 0.090909 | Sprint 2
0.032258 |  | Task 6 | Social | 2019-12-01 | 2019-12-31 | 31 | 22 | 1 | 30 | 3.226% | 3 | 3 | 0.032258 | Sprint 2
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 2
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 2
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 2
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 2
Insert new rows ABOVE this line
| CLIENT DELIVERABLE |  |  | 2019-07-01 | 2019-12-31 | 183 | 132
1 |  | Task 1 | Management | 2019-07-01 | 2019-07-05 | 5 | 5 | 5 | 0 | 100% | 1 | 1 | 1 | Sprint 3
0.93333 |  | Task 2 | Content | 2019-07-01 | 2019-07-15 | 15 | 11 | 14 | 1 | 93.33% | 1 | 1 | 0.93333 | Sprint 3
0.625 |  | Task 3 | Design | 2019-08-01 | 2019-09-01 | 32 | 22 | 20 | 12 | 62.5% | 2 | 2 | 0.625 | Sprint 3
0 |  | Task 4 | Digital | 2019-07-15 | 2019-09-01 | 49 | 35 | 0 | 49 | 0% | 2 | 2 | 0 | Sprint 3
0 |  | Task 5 | Development | 2019-08-22 | 2019-09-01 | 11 | 7 | 0 | 11 | 0% | 3 | 3 | 0 | Sprint 3
0 |  | Task 6 | Social | 2019-12-01 | 2019-12-31 | 31 | 22 | 0 | 31 | 0% | 3 | 3 | 0 | Sprint 3
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 3
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 3
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 3
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 3
Insert new rows ABOVE this line
| CLIENT DELIVERABLE |  |  | 2019-07-01 | 2019-12-31 | 183 | 132
1 |  | Task 1 | Management | 2019-07-01 | 2019-07-05 | 5 | 5 | 5 | 0 | 100% | 1 | 1 | 1 | Sprint 4
0.93333 |  | Task 2 | Content | 2019-07-01 | 2019-07-15 | 15 | 11 | 14 | 1 | 93.33% | 1 | 1 | 0.93333 | Sprint 4
0.625 |  | Task 3 | Design | 2019-08-01 | 2019-09-01 | 32 | 22 | 20 | 12 | 62.5% | 2 | 2 | 0.625 | Sprint 4
0 |  | Task 4 | Digital | 2019-07-15 | 2019-09-01 | 49 | 35 | 0 | 49 | 0% | 2 | 2 | 0 | Sprint 4
0 |  | Task 5 | Development | 2019-08-22 | 2019-09-01 | 11 | 7 | 0 | 11 | 0% | 3 | 3 | 0 | Sprint 4
0 |  | Task 6 | Social | 2019-12-01 | 2019-12-31 | 31 | 22 | 0 | 31 | 0% | 3 | 3 | 0 | Sprint 4
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 4
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 4
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 4
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 4
Insert new rows ABOVE this line
| CLIENT DELIVERABLE |  |  | 2019-07-01 | 2019-12-31 | 183 | 132
1 |  | Task 1 | Management | 2019-07-01 | 2019-07-05 | 5 | 5 | 5 | 0 | 100% | 1 | 1 | 1 | Sprint 5
0.93333 |  | Task 2 | Content | 2019-07-01 | 2019-07-15 | 15 | 11 | 14 | 1 | 93.33% | 1 | 1 | 0.93333 | Sprint 5
0.625 |  | Task 3 | Design | 2019-08-01 | 2019-09-01 | 32 | 22 | 20 | 12 | 62.5% | 2 | 2 | 0.625 | Sprint 5
0 |  | Task 4 | Digital | 2019-07-15 | 2019-09-01 | 49 | 35 | 0 | 49 | 0% | 2 | 2 | 0 | Sprint 5
0 |  | Task 5 | Development | 2019-08-22 | 2019-09-01 | 11 | 7 | 0 | 11 | 0% | 3 | 3 | 0 | Sprint 5
0 |  | Task 6 | Social | 2019-12-01 | 2019-12-31 | 31 | 22 | 0 | 31 | 0% | 3 | 3 | 0 | Sprint 5
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 5
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 5
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 5
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Sprint 5
Insert new rows ABOVE this line
Note on B10: LEGEND - Automatically Indicates: - GREEN Check = 100% DONE - WHITE Circle = In Progress - GRAY Circle = No Progress (Not Started Yet)
Note on F10: Please cut and paste dates as "Special Values" PC: Ctrl+Alt+V, then V MAC: Ctrl + Command + V, then V
Note on G10: Please cut and paste dates as "Special Values" PC: Ctrl+Alt+V, then V MAC: Ctrl + Command + V, then V
Note on L10: User inputs # days completed
Note on M10: If error "X" results, this means "Days Done" cannot be greater than "Days Curation" (total amount of days).
Note on O10: Adjust "DONE %" progress by inputting estimated days done in Column "DAYS DONE"
Note on Q10: KEY LEGEND: - For RED circle, type: 1. - For YELLOW circle, type: 2. - For GREEN circle, type: 3.
Note on S10: KEY LEGEND: - For RED flag, type: 1. - For YELLOW flag, type: 2. - For GREEN flag, type: 3.
Note on U10: LEGEND: Automatically Indicates: - Full Star: 2/3 to 100% Complete. - Half Star: 1/3 to 2/3 Complete. - No Star: 0% to 1/3 Complete.

## WBS Gantt-Chart for Jira
WBS Gantt-Chart for Jira is integrated with Jira and is more feature packed than
this free downloadable version. It also comes with other bonus content.
Watch our Overview Video
Learn More About WBS Gantt-Chart for Jira
https://www.ricksoft-inc.com/wbs-gantt-chart-for-jira/
WBS Gantt-Chart for Jira is loaded with Exceptional Features:
Project Planning
• Version creation
• Saved issue templates
• Modifying an issue
• Issue detail view
• Modify parent-child relations (Drag & drop)
• Sorting the display order of issues (Drag & drop)
• Create dependencies (Drag & drop)
• Workload resource planning
• View schedule in Gantt chart
• Point & click schedule modification
Tracking & Monitoring Stage
• Critical path view
• Milestone tracking
• Four types of task links
• Auto-calculated completion percentage
• Delayed task alert
• Upcoming due date alert
More Features
• Microsoft Project import/export
• One-click Excel export
• Data aggregation by scheduled job
• English, Français, Deutsch, 日本語, 한국어, and Русский

## Terms of Use
https://www.ricksoft-inc.com/wbs-gantt-chart-for-jira/
By Ricksoft-Inc.com
Copyright © Ricksoft, Inc. All Rights Reserved.
This workpaper, including all sheets and associated content, is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template.
Thank you from Ricksoft Inc.
See License Agreement

## 1 (hidden)
SCROLL
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52