## Agile Project Timeline
| AGILE PRODUCT DEVELOPMENT TIMELINE TEMPLATE | [6 empty] | Courtesy of: |  | Complete
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE |  | In Progress
| Beta Release | Richard Tory | 2023-07-01 | 2023-12-11 |  | 42% |  | SCOPE STATEMENT |  | Delayed
Not Started
AT RISK | TASK NAME | FEATURE TYPE | ASSIGNEE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Ron Liu |  | 2023-07-02 | 2023-08-02 | 31 | Complete
| Feature 1 |  | Sharon Kim |  | 2023-07-02 | 2023-08-12 | 41 | Complete
| Feature 2 |  | Franz Fisher |  | 2023-08-15 | 2023-09-12 | 28 | Complete
| Feature 3 |  | Franz Fisher |  | 2023-08-18 | 2023-09-10 | 23 | Complete
| Sprint 2 |  | Franz Fisher |  | 2023-09-09 | 2023-10-12 | 33 | Complete
| Feature 4 |  | Andrew Rai |  | 2023-09-14 | 2023-10-27 | 43 | In Progress
| Feature 5 |  | Ron Liu |  | 2023-09-21 | 2023-10-21 | 30 | In Progress
| Feature 6 |  | Sharon Kim |  | 2023-09-22 | 2023-11-12 | 51 | Delayed
| Sprint 3 |  | Sharon Kim |  | 2023-09-25 | 2023-10-11 | 16 | Delayed
| Feature 7 |  | Ron Liu |  | 2023-09-25 | 2023-11-29 | 65 | Not Started
| Feature 8 |  | Andrew Rai |  | 2023-09-24 | 2023-11-30 | 67 | Not Started
| Feature 9 |  | Franz Fisher |  | 2023-10-02 | 2023-12-09 | 68 | Not Started

## Gantt Chart Planner
Gantt Chart Planner for Confluence is integrated with Confluence and is more feature packed than
the free version. It also comes with bonus content.
Watch our Overview Video
Learn More About Gantt Chart Planner for Confluence
Gantt Chart Planner for Confluence Is Loaded with Exceptional Features:
Easy Gantt Chart Creation
• Work break down structure
• Auto schedule calculation
• Dependencies
• Resource assigning
• Working alendars
• Custom columns
• Jira integration
• Rollup tasks
• View schedule in Gantt chart
• Drag-drop interface
MS Project like Advanced Features
• Critical paths
• Progress lines
• Sharable format export
• Import MS Project file
• CSV export to import Gantt chart into spreadsheets or Jira
• Version history
And More
• Microsoft Project import/export
• Undo/redo
• English, Français, Deutsch, 日本語, 한국어, and Русский

## Terms of Use
https://www.ricksoft-inc.com/gantt-chart-planner/
By Ricksoft-Inc.com
Copyright © Ricksoft, Inc. All Rights Reserved.
This workpaper, including all sheets and associated content, is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template.
Thank you from Ricksoft Inc.
See License Agreement